# 7.7 Stage-by-stage lifecycle checklist (from Module 6)

Standalone artifact. Open AI Governance and Deployment Framework, Version 1.0. Toolkit edition. Licence: CC BY 4.0. One per system; items initialled as completed; gate rows signed per Module 3. Durations are Tier 2 defaults.

Stage 1: Validation (2 to 6 weeks)

☐	Acceptance criteria fixed in the contract schedule before testing (accuracy, worst subgroup gap, operational limits)

☐	Test sample assembled: at least 300 cases, representative, subgroups covered, hard cases included

☐	Sample frozen under Data Steward control; excluded in writing from vendor training

☐	Run completed in a test configuration; results scored against pre-fixed criteria only

☐	Compared against current practice on the same cases

☐	Decision recorded: pass / remediate and retest / renegotiate scope / exit

☐	GATE G2: Data checklist (Module 5) and validation results signed: Data Steward ______ Independent Reviewer ______ Date ______

Stage 2: Shadow mode (minimum 4 weeks and 200 outputs; 6 to 8 weeks if low detectability)

☐	Outputs recorded, nobody acting on them; comparison method defined first

☐	Live alert or exception rate measured against the operational criterion

☐	Real minutes-per-case review cost measured; reviewer time budget set (Module 3.4)

☐	Monitoring baselines captured for every Artifact 6b metric

Stage 3: Pilot (4 to 12 weeks)

☐	One-paragraph pilot definition written first: scope, duration, success criteria, stop criteria with numbers

☐	Oversight design one-pager in force (Module 3.4); reviewers trained on limitations and validation failures

☐	Appeal channel live and notice published (Artifact 6c)

☐	Incident plan and monitoring plan (Artifact 6b) in force

☐	Pilot decision recorded either way

☐	GATE G3 (full go-live): System Owner ______ Independent Reviewer ______ Date ______

Stage 4: Operation (standing)

☐	Monthly monitoring review and summary to System Owner; weekly glance if low detectability

☐	Monthly unflagged-case audit (20 cases or 2 percent); quarterly outcome reconciliation

☐	Appeals log read monthly beside the metrics

☐	Every update notice through the 6.7 routine; change log current; frozen test set or prompt set re-run on model changes

☐	GATE G4 (every 12 months and on trigger): revalidation passed, roles filled, thresholds reviewed: System Owner ______ Date ______

Stage 5: Decommissioning (2 to 8 weeks)

☐	Trigger and decision recorded

☐	Fallback confirmed working and staffed before switch-off

☐	Users, operators, and (where relevant) affected persons informed

☐	Export received and verified; decision records retained per local retention rules

☐	Vendor deletion certificate on file: Data Steward ______ Date ______

☐	Access closed item by item; register entry closed; one page of lessons filed with the procurement templates

Document control. Document version: ____________ Prepared by: ____________ Last updated: ____________ Next review: ____________